## Bid Analysis
| BID ANALYSIS - SUMMARY |  |  |  | CONFIDENTIAL
CLIENT : | Glencore Technology |  |  |  | BID ANALYSIS
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  | JOB NO.: | 14734A
EQUIPMENT PACKAGE | ASPECT | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
TRF — Tilting Refining Furnace | Technical compliance | Compliant, 1/34 not specified | Fully compliant | Compliant, 1/34 not specified | 13 deviation(s), 0 unspecified of 34
| Commercial verdict | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations
TBRC — Top Blown Rotary Converter | Technical compliance | Compliant, 8/55 not specified | Fully compliant | Compliant, 8/55 not specified | 14 deviation(s), 8 unspecified of 55
| Commercial verdict | Not Acceptable — bidder fails qualification gate | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations
TSF — Top Submerged Lance Smelting Furnace | Technical compliance | Fully compliant | Compliant, 1/32 not specified | Compliant, 1/32 not specified | 13 deviation(s), 1 unspecified of 32
| Commercial verdict | Acceptable subject to considering deviations | Not Acceptable — bidder fails qualification gate | Acceptable subject to considering deviations | Not Acceptable — bidder fails qualification gate
TRF_CASTING_WHEEL — TRF Casting Wheel | Technical compliance | Fully compliant | 12 deviation(s), 0 unspecified of 30 | 12 deviation(s), 0 unspecified of 30 | 12 deviation(s), 0 unspecified of 30
| Commercial verdict | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TRF CE
|  | BID ANALYSIS - COMMERCIAL |  |  |  |  | CONFIDENTIAL
CLIENT : | Glencore Technology | [5 empty] | TABLE - 2A
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  |  |  | JOB NO.: | 14734A
RECOMMENDATION FOR AWARD OF JOB
SL NO. | BIDDERS REPLIES / QUOTE → |  | VENDOR RESPONSES |  |  |  | REMARKS
| DATA REQUIRED TO BE FURNISHED BY BIDDERS AS PER TENDER ↓ | TENDER REQUIREMENT ↓ | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | Bid Qualification | Net Worth | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
|  | Annual Turnover | QUALIFIED: Avg annual turnover INR 1072 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 926 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 998 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 853 Cr over last 3 FY | All bidders qualified.
|  | Net Profit (PAT) | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
2 | Proposal compliance | EMD of INR XXX (Indian Rupees YYYYY only) for Indian Bidders or USD XXXX (U.S. Dollars YYYYY) for Foreign Bidders. (Annexure X) | Deviation: EMD value short of tender requirement | Compliant: EMD submitted via BG dated 12-Apr-2026 | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Power of Attorney in favour of the person who has signed the bid | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | RFQ acceptance | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Compliant: RFQ terms accepted | Compliant: RFQ terms accepted | Deviation: M/s. JNK India Pvt. Ltd.
|  | Deviation list | Compliant: Deviation list submitted | Subject to deviation: partial list | Subject to deviation: partial list | Compliant: Deviation list submitted | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
3 | Price Evaluation | Total price (Lump sum) | INR 7,72,00,000 Lump sum | INR 9,76,00,000 Lump sum | INR 9,98,00,000 Lump sum | INR 4,53,00,000 Lump sum | Compliant across bidders.
|  | Itemised pricing | Deviation: itemised pricing not provided | Deviation: itemised pricing not provided | Compliant: item-wise breakdown in Annex C | Deviation: itemised pricing not provided | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Front-End Engineering & Design (FEED) price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Core furnace package price (Groups 100-900) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Recommended spares price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Shipping, Installation & Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Hot Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | 2-year O&M spares & consumables | 2-year O&M spares: INR 2.2 Cr | 2-year O&M spares: INR 1.6 Cr | 2-year O&M spares: INR 1.8 Cr | 2-year O&M spares: INR 2.3 Cr | Compliant across bidders.
|  | Quote Currency (INR / USD / EUR / GBP) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
4 | Commercial Terms | Delivery terms (FCA) | Compliant: FCA Mumbai | Deviation: quoted on CIF basis | Deviation: quoted on CIF basis | Compliant: FCA Mumbai | Deviation: M/s. JNK India Pvt. Ltd., M/s. Outotec
|  | Delivery schedule | 32 weeks ex-works from PO | 26 weeks ex-works from PO | 38 weeks ex-works from PO | 33 weeks ex-works from PO | Compliant across bidders.
|  | Payment terms | Subject to deviation: requesting 20% advance | Subject to deviation: requesting 20% advance | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Subject to deviation: requesting 20% advance | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Payment milestone structure (PO / FAT / Commissioning split) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Taxes & duties | Subject to deviation: taxes included in price | Subject to deviation: taxes included in price | Compliant: GST 18% extra | Compliant: GST 18% extra | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd.
|  | Quote validity | 112 days from bid due date | 96 days from bid due date | 108 days from bid due date | 103 days from bid due date | Compliant across bidders.
|  | Late payment interest rate (per month) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
5 | Contract Conditions | Warranty (48 months) | Deviation: 24 months only | Compliant: 48 months from PAC | Compliant: 48 months from PAC | Compliant: 48 months from PAC | Deviation: M/s. ISGEC Heavy Engineering Ltd.
|  | Warranty reference point (FAT / PAC / Commissioning) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Warranty exclusions list (refractories, lances, etc.) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Completion period | 16 months from PO date | 12 months from PO date | 12 months from PO date | 13 months from PO date | Compliant across bidders.
|  | Performance Bank Guarantee (PBG) | Compliant: 10% PBG | Subject to deviation: 5% PBG only | Compliant: 10% PBG | Subject to deviation: 5% PBG only | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Liquidated damages | Compliant: 0.5%/wk capped 10% | Compliant: 0.5%/wk capped 10% | Subject to deviation: LD cap of 5% | Subject to deviation: LD cap of 5% | Deviation: M/s. Outotec, M/s. Mitsui Mining & Smelting
6 | Performance Guarantees (Technical) | Firing rate guarantee (MW for combustion lance) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Working volume guarantee (litres at nominal %) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Rotation speed range guarantee (RPM min-max) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Throughput / batch time guarantee |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Performance acceptance test criteria explicitly stated |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Field performance test arrangement (FAT / on-site) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
7 | Scope & Risks | Scope inclusions | Deviation: civil works excluded | Compliant: full SoW | Compliant: full SoW | Deviation: civil works excluded | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
|  | Scope exclusions | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Compliant across bidders.
|  | Refractory scope (vendor-supplied vs separate) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Deviations from RFQ | See Annex E — 4 commercial deviations | See Annex E — 3 commercial deviations | See Annex E — 5 commercial deviations | See Annex E — 5 commercial deviations | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Installation & commissioning | Deviation: I&C as separate optional package | Compliant: I&C included | Deviation: I&C as separate optional package | Compliant: I&C included | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
|  | Insurance liability terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | IP / Technology licence terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
8 | Final Evaluation | Commercial acceptability | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Risk level | Medium | Medium | Medium | Medium | Compliant across bidders.
9 | Commercial Acceptability: Acceptable / Not Acceptable |  | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TRF TE
|  | BID ANALYSIS - TECHNICAL | [6 empty] | CONFIDENTIAL
CLIENT : | Glencore Technology |  |  |  |  | EQUIPMENT/SYSTEM: | TRF |  | TABLE - 3
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  | ENQ. NO.: | TCE/2026/ENQ/4471 | JOB NO.: | 14734A |  | SHEET 3 OF 9
SL.NO. | DETAILS | UNIT | BIDDER >> |  | VENDOR RESPONSES |  |  |  | REMARKS
|  |  | TCE SPEC. ↓ | Reference Value (TCE Study) | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | FURNACE DESIGN | No. | Number of Furnaces | 1 | 0.9757 | 0.9744 | 0.9846 | 1.0722 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | - | Furnace Type | Tilting Refining Furnace | Tilting Refining Furnace (vendor compliant) | Tilting Refining Furnace (vendor compliant) | Tilting Refining Furnace (vendor compliant) | Tilting Refining Furnace | All vendors compliant with TCE spec.
|  | - | Capacity | 243 TPD/ 7280 TPM | 243 TPD/ 7280 TPM (vendor compliant) | 243 TPD/ 7280 TPM (vendor compliant) | 243 TPD/ 7280 TPM (vendor compliant) | 243 TPD/ 7280 TPM | All vendors compliant with TCE spec.
2 | PROCESS CYCLE | hrs | Stage-1 Oxidation Time | 4.82 | 4.7028 | 4.6966 | 4.746 | 5.1678 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | hrs | Stage-2 Reduction Time | 0.309 | 0.3015 | 0.3011 | 0.3043 | 0.3313 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | hrs | Total Reaction Time | 5.13 | 5.0052 | 4.9987 | 5.0512 | 5.5002 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | hrs | Loading / Unloading Time | Vendor to specify | Vendor to specify (vendor compliant) | Vendor to specify (vendor compliant) | Vendor to specify (vendor compliant) | Vendor to specify | All vendors compliant with TCE spec.
|  | hrs | Total Cycle Time Available | 9.1 | 8.8787 | 8.867 | 8.9602 | 9.7567 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
3 | OPERATING CONDITIONS | - | Fuel Type | Natural Gas | Natural Gas (vendor compliant) | Natural Gas (vendor compliant) | Natural Gas (vendor compliant) | Natural Gas | All vendors compliant with TCE spec.
|  | No. | Number of Tuyeres | 2 | 1.9514 | 1.9488 | 1.9693 | 2.1443 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | Nm3/h | Tuyere Gas Rate (Instantaneous) | 900 | 878.112 | 876.96 | 886.176 | 964.944 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | % | Tuyere Efficiency | 60 | 58.5408 | 58.464 | 59.0784 | 64.3296 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | - | Operating Temperature Range |  |  | Vendor to specify |  | Vendor to specify | Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
4 | STAGE CHEMISTRY | wt% | Stage-1 Copper in Slag | 60 | 58.5408 | 58.464 | 59.0784 | 64.3296 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | ppm | Stage-1 Oxygen in Bath | 4500 | 4390.56 | 4384.8 | 4430.88 | 4824.72 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | ppm | Stage-2 Oxygen in Bath | 1500 | 1463.52 | 1461.6 | 1476.96 | 1608.24 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
|  | ppm | Arsenic in Anode | 1300 | 1268.384 | 1266.72 | 1280.032 | 1393.808 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
5 | MECHANICAL FEATURES | - | Furnace Lining & Binding System | Backstay & binding system | Backstay & binding system (vendor compliant) | Backstay & binding system (vendor compliant) | Backstay & binding system (vendor compliant) | Backstay & binding system | All vendors compliant with TCE spec.
|  | - | Freeboard Burners | Natural gas fired | Natural gas fired (vendor compliant) | Natural gas fired (vendor compliant) | Natural gas fired (vendor compliant) | Natural gas fired | All vendors compliant with TCE spec.
|  | - | Refining Tuyeres | Sidewall mounted | Sidewall mounted (vendor compliant) | Sidewall mounted (vendor compliant) | Sidewall mounted (vendor compliant) | Sidewall mounted | All vendors compliant with TCE spec.
|  | - | Charging System | Scrap boat & liquid launder | Scrap boat & liquid launder (vendor compliant) | Scrap boat & liquid launder (vendor compliant) | Scrap boat & liquid launder (vendor compliant) | Scrap boat & liquid launder | All vendors compliant with TCE spec.
|  | - | Tilting Mechanism | Skimming & pouring by tilting | Skimming & pouring by tilting (vendor compliant) | Skimming & pouring by tilting (vendor compliant) | Skimming & pouring by tilting (vendor compliant) | Skimming & pouring by tilting | All vendors compliant with TCE spec.
6 | CASTING WHEEL | - | Anode Casting Method | Casting wheel | Casting wheel (vendor compliant) | Casting wheel (vendor compliant) | Casting wheel (vendor compliant) | Casting wheel | All vendors compliant with TCE spec.
|  | - | Mould Cooling | Air + Water cooling | Air + Water cooling (vendor compliant) | Air + Water cooling (vendor compliant) | Air + Water cooling (vendor compliant) | Air + Water cooling | All vendors compliant with TCE spec.
|  | - | Mould Wash Type | Yotai Coat COAT-NCF | Yotai Coat COAT-NCF (vendor compliant) | Yotai Coat COAT-NCF (vendor compliant) | Yotai Coat COAT-NCF (vendor compliant) | Yotai Coat COAT-NCF | All vendors compliant with TCE spec.
|  | kg/t Cu | Mould Wash Consumption | 0.15 | 0.1464 | 0.1462 | 0.1477 | 0.1608 | M/s. Mitsui Mining & Smelting: +7.2% vs TCE
7 | OFF-GAS TREATMENT SYSTEM | - | Afterburner / Post Combustion | Refractory lined | Refractory lined (vendor compliant) | Refractory lined (vendor compliant) | Refractory lined (vendor compliant) | Refractory lined | All vendors compliant with TCE spec.
|  | - | Gas Cooling / Dilution | Dilution air | Dilution air (vendor compliant) | Dilution air (vendor compliant) | Dilution air (vendor compliant) | Dilution air | All vendors compliant with TCE spec.
|  | - | Dedusting System | Baghouse | Baghouse (vendor compliant) | Baghouse (vendor compliant) | Baghouse (vendor compliant) | Baghouse | All vendors compliant with TCE spec.
|  | - | Dust Handling | Recycle / bleed | Recycle / bleed (vendor compliant) | Recycle / bleed (vendor compliant) | Recycle / bleed (vendor compliant) | Recycle / bleed | All vendors compliant with TCE spec.
8 | INTEGRATION | - | Feed from TBRC | Raw copper | Raw copper (vendor compliant) | Raw copper (vendor compliant) | Raw copper (vendor compliant) | Raw copper | All vendors compliant with TCE spec.
|  | - | Copper Scrap Charging | High % solid scrap | High % solid scrap (vendor compliant) | High % solid scrap (vendor compliant) | High % solid scrap (vendor compliant) | High % solid scrap | All vendors compliant with TCE spec.
|  | - | Anode Dispatch | ISAKIDD™ Tankhouse | ISAKIDD™ Tankhouse (vendor compliant) | ISAKIDD™ Tankhouse (vendor compliant) | ISAKIDD™ Tankhouse (vendor compliant) | ISAKIDD™ Tankhouse | All vendors compliant with TCE spec.
|  | - | Skim & Reject Recycling | ISACYCLE™ | ISACYCLE™ (vendor compliant) | ISACYCLE™ (vendor compliant) | ISACYCLE™ (vendor compliant) | ISACYCLE™ | All vendors compliant with TCE spec.
9 | LIST OF DOCUMENT
A |  |  | Process Description |  | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
B |  |  | Substance list |  | ✗ Missing | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
C |  |  | Plant emission list |  | ✗ Missing | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
D |  |  | Delivery lead time |  | ✓ Included | ✓ Included | ✗ Missing | ✗ Missing | Missing from: M/s. Outotec, M/s. Mitsui Mining & Smelting
E |  |  | Equipment List including noise emissions |  | ✗ Missing | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
F |  |  | Plant equipment 3D Model |  | ✗ Missing | ✗ Missing | ✓ Included | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd.
G |  |  | Loading Diagrams |  | ✓ Included | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
H |  |  | General Arrangement Drawings |  | ✗ Missing | ✓ Included | ✓ Included | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd.
I |  |  | Electrical Consumer List |  | ✗ Missing | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
J |  |  | I/O Count based on past projects |  | ✓ Included | ✓ Included | ✗ Missing | ✗ Missing | Missing from: M/s. Outotec, M/s. Mitsui Mining & Smelting
K |  |  | Typical P&ID based on past projects |  | ✓ Included | ✓ Included | ✗ Missing | ✗ Missing | Missing from: M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TBRC CE
|  | BID ANALYSIS - COMMERCIAL |  |  |  |  | CONFIDENTIAL
CLIENT : | Glencore Technology | [5 empty] | TABLE - 4A
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  |  |  | JOB NO.: | 14734A
RECOMMENDATION FOR AWARD OF JOB
SL NO. | BIDDERS REPLIES / QUOTE → |  | VENDOR RESPONSES |  |  |  | REMARKS
| DATA REQUIRED TO BE FURNISHED BY BIDDERS AS PER TENDER ↓ | TENDER REQUIREMENT ↓ | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | Bid Qualification | Net Worth | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
|  | Annual Turnover | NOT QUALIFIED: figures do not meet tender threshold | QUALIFIED: Avg annual turnover INR 1126 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 1061 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 869 Cr over last 3 FY | NOT QUALIFIED: M/s. ISGEC Heavy Engineering Ltd.
|  | Net Profit (PAT) | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
2 | Proposal compliance | EMD of INR XXX (Indian Rupees YYYYY only) for Indian Bidders or USD XXXX (U.S. Dollars YYYYY) for Foreign Bidders. (Annexure X) | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Power of Attorney in favour of the person who has signed the bid | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: PoA not notarised | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | RFQ acceptance | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Deviation list | Subject to deviation: partial list | Subject to deviation: partial list | Compliant: Deviation list submitted | Compliant: Deviation list submitted | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
3 | Price Evaluation | Total price (Lump sum) | INR 7,52,00,000 Lump sum | INR 9,76,00,000 Lump sum | INR 12,61,00,000 Lump sum | INR 4,69,00,000 Lump sum | Compliant across bidders.
|  | Itemised pricing | Compliant: item-wise breakdown in Annex C | Compliant: item-wise breakdown in Annex C | Deviation: itemised pricing not provided | Compliant: item-wise breakdown in Annex C | Deviation: M/s. Outotec
|  | Front-End Engineering & Design (FEED) price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Core furnace package price (Groups 100-900) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Recommended spares price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Shipping, Installation & Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Hot Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | 2-year O&M spares & consumables | 2-year O&M spares: INR 2.2 Cr | 2-year O&M spares: INR 1.6 Cr | 2-year O&M spares: INR 1.1 Cr | 2-year O&M spares: INR 2.9 Cr | Compliant across bidders.
|  | Quote Currency (INR / USD / EUR / GBP) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
4 | Commercial Terms | Delivery terms (FCA) | Deviation: quoted on CIF basis | Deviation: quoted on CIF basis | Deviation: quoted on CIF basis | Compliant: FCA Mumbai | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
|  | Delivery schedule | 32 weeks ex-works from PO | 26 weeks ex-works from PO | 21 weeks ex-works from PO | 29 weeks ex-works from PO | Compliant across bidders.
|  | Payment terms | Subject to deviation: requesting 20% advance | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Subject to deviation: requesting 20% advance | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
|  | Payment milestone structure (PO / FAT / Commissioning split) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Taxes & duties | Subject to deviation: taxes included in price | Subject to deviation: taxes included in price | Compliant: GST 18% extra | Compliant: GST 18% extra | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd.
|  | Quote validity | 112 days from bid due date | 96 days from bid due date | 111 days from bid due date | 109 days from bid due date | Compliant across bidders.
|  | Late payment interest rate (per month) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
5 | Contract Conditions | Warranty (48 months) | Deviation: 24 months only | Compliant: 48 months from PAC | Compliant: 48 months from PAC | Compliant: 48 months from PAC | Deviation: M/s. ISGEC Heavy Engineering Ltd.
|  | Warranty reference point (FAT / PAC / Commissioning) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Warranty exclusions list (refractories, lances, etc.) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Completion period | 16 months from PO date | 12 months from PO date | 15 months from PO date | 13 months from PO date | Compliant across bidders.
|  | Performance Bank Guarantee (PBG) | Subject to deviation: 5% PBG only | Subject to deviation: 5% PBG only | Subject to deviation: 5% PBG only | Subject to deviation: 5% PBG only | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Liquidated damages | Compliant: 0.5%/wk capped 10% | Compliant: 0.5%/wk capped 10% | Compliant: 0.5%/wk capped 10% | Compliant: 0.5%/wk capped 10% | Compliant across bidders.
6 | Performance Guarantees (Technical) | Firing rate guarantee (MW for combustion lance) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Working volume guarantee (litres at nominal %) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Rotation speed range guarantee (RPM min-max) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Throughput / batch time guarantee |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Performance acceptance test criteria explicitly stated |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Field performance test arrangement (FAT / on-site) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
7 | Scope & Risks | Scope inclusions | Deviation: civil works excluded | Compliant: full SoW | Deviation: civil works excluded | Compliant: full SoW | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
|  | Scope exclusions | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Compliant across bidders.
|  | Refractory scope (vendor-supplied vs separate) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Deviations from RFQ | See Annex E — 4 commercial deviations | See Annex E — 3 commercial deviations | See Annex E — 3 commercial deviations | See Annex E — 6 commercial deviations | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Installation & commissioning | Deviation: I&C as separate optional package | Compliant: I&C included | Compliant: I&C included | Deviation: I&C as separate optional package | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
|  | Insurance liability terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | IP / Technology licence terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
8 | Final Evaluation | Commercial acceptability | Not Acceptable | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Risk level | High | Medium | Medium | Medium | Compliant across bidders.
9 | Commercial Acceptability: Acceptable / Not Acceptable |  | Not Acceptable — bidder fails qualification gate | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TBRC TE
|  | BID ANALYSIS - TECHNICAL | [6 empty] | CONFIDENTIAL
CLIENT : | Glencore Technology |  |  |  |  | EQUIPMENT/SYSTEM: | TBRC |  | TABLE - 5
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  | ENQ. NO.: | TCE/2026/ENQ/4471 | JOB NO.: | 14734A |  | SHEET 5 OF 9
SL.NO. | DETAILS | UNIT | BIDDER >> |  | VENDOR RESPONSES |  |  |  | REMARKS
|  |  | TCE SPEC. ↓ | Reference Value (TCE Study) | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | CONVERTER DESIGN | No. | Number of Converters | 1 | 1.0075 | 1.0347 | 0.9974 | 1.0566 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | - | Converter Type | Top Blown Rotary Converter | Top Blown Rotary Converter | Top Blown Rotary Converter | Top Blown Rotary Converter (vendor compliant) | Top Blown Rotary Converter | All vendors compliant with TCE spec.
|  | t | Capacity (heat size) | TBD per TCE study |  | Vendor to specify |  |  | Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | - | Spare Shell Included | Yes | Yes | Yes | Yes (vendor compliant) | Yes | All vendors compliant with TCE spec.
2 | VESSEL SIZING | mm | Vessel Inner Diameter (refractory ID) | TBD per TCE study |  | Vendor to specify |  |  | Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | mm | Vessel Outer Diameter (shell OD) | TBD per TCE study |  | Vendor to specify |  |  | Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | mm | Vessel Length | TBD per TCE study |  | Vendor to specify |  |  | Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | L | Total Vessel Volume (inside refractory) | TBD per TCE study |  | Vendor to specify |  |  | M/s. JNK India Pvt. Ltd.: non-numeric ('Vendor to specify'); Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | L | Nominal Working Volume (33% capacity) | TBD per TCE study |  | Vendor to specify |  |  | M/s. JNK India Pvt. Ltd.: non-numeric ('Vendor to specify'); Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | L | Maximum Volume (50% capacity) | TBD per TCE study |  | Vendor to specify |  |  | M/s. JNK India Pvt. Ltd.: non-numeric ('Vendor to specify'); Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | m3 | Bath Volume at Design Capacity | TBD per TCE study |  | Vendor to specify |  |  | M/s. JNK India Pvt. Ltd.: non-numeric ('Vendor to specify'); Not specified by M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | - | Vessel Shell Material | P265GH or equivalent | P265GH or equivalent | P265GH or equivalent | P265GH or equivalent (vendor compliant) | P265GH or equivalent | All vendors compliant with TCE spec.
|  | mm | Vessel Shell Thickness | 25 | 25.188 | 25.868 | 24.936 | 26.414 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
3 | PROCESS CYCLE | hrs | Smelting / Firing Time | 2.5 | 2.5188 | 2.5868 | 2.4936 | 2.6414 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | hrs | Converting Time | 3 | 3.0226 | 3.1042 | 2.9923 | 3.1697 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | hrs | Tapping Time | 0.5 | 0.5038 | 0.5174 | 0.4987 | 0.5283 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | hrs | Total Batch Time | 7.11 | 7.1635 | 7.3569 | 7.0918 | 7.5121 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | deg | Tilt Angle for Pouring | 25 | 25.188 | 25.868 | 24.936 | 26.414 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
4 | PERFORMANCE GUARANTEES | MW | Firing Rate (combustion lance) | 1.8-2.0 | 1.8-2.0 | 1.8-2.0 | 1.8-2.0 (vendor compliant) | 1.8-2.0 | All vendors compliant with TCE spec.
|  | Nm3/h | Overblow O2 Flow Rate | 400 | 403.008 | 413.888 | 398.976 | 422.624 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | rpm | Rotation Speed Range | 1-15 | 1-15 | 1-15 | 1-15 (vendor compliant) | 1-15 | All vendors compliant with TCE spec.
|  | % | Oxygen Enrichment in Lance | 100 | 100.752 | 103.472 | 99.744 | 105.656 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | - | Performance Test Acceptance Criteria Stated | Yes | Yes | Yes | Yes (vendor compliant) | Yes | All vendors compliant with TCE spec.
5 | OPERATING CONDITIONS | - | Lance Gas Type | Oxy-fuel (natural gas + O2) | Oxy-fuel (natural gas + O2) | Oxy-fuel (natural gas + O2) | Oxy-fuel (natural gas + O2) (vendor compliant) | Oxy-fuel (natural gas + O2) | All vendors compliant with TCE spec.
|  | MW | Burner Liberated Power | 1.8-2.0 | 1.8-2.0 | 1.8-2.0 | 1.8-2.0 (vendor compliant) | 1.8-2.0 | All vendors compliant with TCE spec.
|  | Nm3/h | Lance Gas Flow Rate | 5000 | 5037.6 | 5173.6 | 4987.2 | 5282.8 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | °C | Operating Temperature Range | 1200-1350 | 1200-1350 | 1200-1350 | 1200-1350 (vendor compliant) | 1200-1350 | All vendors compliant with TCE spec.
6 | STAGE CHEMISTRY | wt% | Matte Grade (Cu in matte) | 70 | 70.5264 | 72.4304 | 69.8208 | 73.9592 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | wt% | Slag Cu Content (final) | 1.5 | 1.5113 | 1.5521 | 1.4962 | 1.5848 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | - | Fe/SiO2 Ratio in Slag | 1.4 | 1.4105 | 1.4486 | 1.3964 | 1.4792 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
|  | ppm | Sulphur in Blister Copper | 200 | 201.504 | 206.944 | 199.488 | 211.312 | M/s. Mitsui Mining & Smelting: +5.7% vs TCE
7 | MECHANICAL FEATURES | - | Refractory Lining System | Mag-chrome basic brick | Mag-chrome basic brick | Mag-chrome basic brick | Mag-chrome basic brick (vendor compliant) | Mag-chrome basic brick | All vendors compliant with TCE spec.
|  | - | Refractory Supplier | RHI / equivalent | RHI / equivalent | RHI / equivalent | RHI / equivalent (vendor compliant) | RHI / equivalent | All vendors compliant with TCE spec.
|  | - | Refractory Included in Vendor Scope | Yes | Yes | Yes | Yes (vendor compliant) | Yes | All vendors compliant with TCE spec.
|  | - | Lance Insertion Mechanism | Water-cooled retractable, top-mounted | Water-cooled retractable, top-mounted | Water-cooled retractable, top-mounted | Water-cooled retractable, top-mounted (vendor compliant) | Water-cooled retractable, top-mounted | All vendors compliant with TCE spec.
|  | - | Metallurgical Oxygen Lance | Water-cooled retractable, submersible | Water-cooled retractable, submersible | Water-cooled retractable, submersible | Water-cooled retractable, submersible (vendor compliant) | Water-cooled retractable, submersible | All vendors compliant with TCE spec.
|  | - | Vessel Tilting Mechanism | Bevel gearbox on gimbal, hydraulic | Bevel gearbox on gimbal, hydraulic | Bevel gearbox on gimbal, hydraulic | Bevel gearbox on gimbal, hydraulic (vendor compliant) | Bevel gearbox on gimbal, hydraulic | All vendors compliant with TCE spec.
|  | - | Gimbal Frame | Octagonal box-section, stress relieved | Octagonal box-section, stress relieved | Octagonal box-section, stress relieved | Octagonal box-section, stress relieved (vendor compliant) | Octagonal box-section, stress relieved | All vendors compliant with TCE spec.
|  | - | Charging System | Semi-continuous pneumatic hopper | Semi-continuous pneumatic hopper | Semi-continuous pneumatic hopper | Semi-continuous pneumatic hopper (vendor compliant) | Semi-continuous pneumatic hopper | All vendors compliant with TCE spec.
|  | - | Control System | Siemens PLC + HMI touchscreen | Siemens PLC + HMI touchscreen | Siemens PLC + HMI touchscreen | Siemens PLC + HMI touchscreen (vendor compliant) | Siemens PLC + HMI touchscreen | All vendors compliant with TCE spec.
8 | BALANCE OF PLANT | - | Hygiene Enclosure | Included with fume extraction | Included with fume extraction | Included with fume extraction | Included with fume extraction (vendor compliant) | Included with fume extraction | All vendors compliant with TCE spec.
|  | - | Closed Loop Water Cooling | Included (pumps, heat exchangers) | Included (pumps, heat exchangers) | Included (pumps, heat exchangers) | Included (pumps, heat exchangers) (vendor compliant) | Included (pumps, heat exchangers) | All vendors compliant with TCE spec.
|  | - | Gas Fuel Train (EN 746-2) | Included | Included | Included | Included (vendor compliant) | Included | All vendors compliant with TCE spec.
|  | - | Vessel Exchange Trolley | Included | Included | Included | Included (vendor compliant) | Included | All vendors compliant with TCE spec.
|  | - | Bricking Platform | Included | Included | Included | Included (vendor compliant) | Included | All vendors compliant with TCE spec.
|  | - | Gas Booster | If required (~1.5 Bar.g) | If required (~1.5 Bar.g) | If required (~1.5 Bar.g) | If required (~1.5 Bar.g) (vendor compliant) | If required (~1.5 Bar.g) | All vendors compliant with TCE spec.
|  | - | Gas Cleaning Equipment | Baghouse + ID fan + stack | Baghouse + ID fan + stack | Baghouse + ID fan + stack | Baghouse + ID fan + stack (vendor compliant) | Baghouse + ID fan + stack | All vendors compliant with TCE spec.
|  | - | Access Platforms | Per BS EN 1090 EXC 2 | Per BS EN 1090 EXC 2 | Per BS EN 1090 EXC 2 | Per BS EN 1090 EXC 2 (vendor compliant) | Per BS EN 1090 EXC 2 | All vendors compliant with TCE spec.
9 | TAPPING & SLAG HANDLING | - | Tap Hole Design | Water-cooled Cu jacket | Water-cooled Cu jacket | Water-cooled Cu jacket | Water-cooled Cu jacket (vendor compliant) | Water-cooled Cu jacket | All vendors compliant with TCE spec.
|  | - | Slag/Metal Mould System | Pouring into winched refractory-lined moulds | Pouring into winched refractory-lined moulds | Pouring into winched refractory-lined moulds | Pouring into winched refractory-lined moulds (vendor compliant) | Pouring into winched refractory-lined moulds | All vendors compliant with TCE spec.
|  | - | Matte Transfer | Ladle to TRF | Ladle to TRF | Ladle to TRF | Ladle to TRF (vendor compliant) | Ladle to TRF | All vendors compliant with TCE spec.
10 | INTEGRATION | - | Feed Source | Concentrate + flux + scrap | Concentrate + flux + scrap | Concentrate + flux + scrap | Concentrate + flux + scrap (vendor compliant) | Concentrate + flux + scrap | All vendors compliant with TCE spec.
|  | - | Downstream Routing | Blister → TRF for fire refining | Blister → TRF for fire refining | Blister → TRF for fire refining | Blister → TRF for fire refining (vendor compliant) | Blister → TRF for fire refining | All vendors compliant with TCE spec.
|  | - | Slag Destination | Slag treatment circuit | Slag treatment circuit | Slag treatment circuit | Slag treatment circuit (vendor compliant) | Slag treatment circuit | All vendors compliant with TCE spec.
|  | - | Dust Recycle | Back to TBRC feed | Back to TBRC feed | Back to TBRC feed | Back to TBRC feed (vendor compliant) | Back to TBRC feed | All vendors compliant with TCE spec.
11 | LIST OF DOCUMENT
A |  |  | Process Description |  | ✗ Missing | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
B |  |  | Substance list |  | ✓ Included | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. Outotec
C |  |  | Plant emission list |  | ✓ Included | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
D |  |  | Delivery lead time |  | ✗ Missing | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
E |  |  | Equipment List including noise emissions |  | ✓ Included | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. Mitsui Mining & Smelting
F |  |  | Plant equipment 3D Model |  | ✗ Missing | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
G |  |  | Loading Diagrams |  | ✗ Missing | ✓ Included | ✓ Included | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd.
H |  |  | General Arrangement Drawings |  | ✗ Missing | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec
I |  |  | Electrical Consumer List |  | ✗ Missing | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
J |  |  | I/O Count based on past projects |  | ✓ Included | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. Mitsui Mining & Smelting
K |  |  | Typical P&ID based on past projects |  | ✓ Included | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TSF CE
|  | BID ANALYSIS - COMMERCIAL |  |  |  |  | CONFIDENTIAL
CLIENT : | Glencore Technology | [5 empty] | TABLE - 6A
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  |  |  | JOB NO.: | 14734A
RECOMMENDATION FOR AWARD OF JOB
SL NO. | BIDDERS REPLIES / QUOTE → |  | VENDOR RESPONSES |  |  |  | REMARKS
| DATA REQUIRED TO BE FURNISHED BY BIDDERS AS PER TENDER ↓ | TENDER REQUIREMENT ↓ | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | Bid Qualification | Net Worth | QUALIFIED: positive per FY2024-25 audited annual report | NOT QUALIFIED: figures do not meet tender threshold | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | NOT QUALIFIED: M/s. JNK India Pvt. Ltd.
|  | Annual Turnover | QUALIFIED: Avg annual turnover INR 938 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 830 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 988 Cr over last 3 FY | NOT QUALIFIED: figures do not meet tender threshold | NOT QUALIFIED: M/s. Mitsui Mining & Smelting
|  | Net Profit (PAT) | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
2 | Proposal compliance | EMD of INR XXX (Indian Rupees YYYYY only) for Indian Bidders or USD XXXX (U.S. Dollars YYYYY) for Foreign Bidders. (Annexure X) | Compliant: EMD submitted via BG dated 12-Apr-2026 | Compliant: EMD submitted via BG dated 12-Apr-2026 | Compliant: EMD submitted via BG dated 12-Apr-2026 | Deviation: EMD value short of tender requirement | Deviation: M/s. Mitsui Mining & Smelting
|  | Power of Attorney in favour of the person who has signed the bid | Deviation: PoA not notarised | Deviation: PoA not notarised | Compliant: PoA in favour of signatory attached | Compliant: PoA in favour of signatory attached | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd.
|  | RFQ acceptance | Subject to deviation: noted in Annex D | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Compliant: RFQ terms accepted | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
|  | Deviation list | Subject to deviation: partial list | Compliant: Deviation list submitted | Subject to deviation: partial list | Subject to deviation: partial list | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
3 | Price Evaluation | Total price (Lump sum) | INR 5,88,00,000 Lump sum | INR 13,80,00,000 Lump sum | INR 11,88,00,000 Lump sum | INR 4,53,00,000 Lump sum | Compliant across bidders.
|  | Itemised pricing | Compliant: item-wise breakdown in Annex C | Compliant: item-wise breakdown in Annex C | Deviation: itemised pricing not provided | Compliant: item-wise breakdown in Annex C | Deviation: M/s. Outotec
|  | Front-End Engineering & Design (FEED) price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Core furnace package price (Groups 100-900) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Recommended spares price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Shipping, Installation & Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Hot Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | 2-year O&M spares & consumables | 2-year O&M spares: INR 3.8 Cr | 2-year O&M spares: INR 2.0 Cr | 2-year O&M spares: INR 3.8 Cr | 2-year O&M spares: INR 2.3 Cr | Compliant across bidders.
|  | Quote Currency (INR / USD / EUR / GBP) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
4 | Commercial Terms | Delivery terms (FCA) | Compliant: FCA Mumbai | Deviation: quoted on CIF basis | Compliant: FCA Mumbai | Deviation: quoted on CIF basis | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Delivery schedule | 38 weeks ex-works from PO | 30 weeks ex-works from PO | 28 weeks ex-works from PO | 33 weeks ex-works from PO | Compliant across bidders.
|  | Payment terms | Subject to deviation: requesting 20% advance | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Subject to deviation: requesting 20% advance | Subject to deviation: requesting 20% advance | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Payment milestone structure (PO / FAT / Commissioning split) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Taxes & duties | Subject to deviation: taxes included in price | Subject to deviation: taxes included in price | Subject to deviation: taxes included in price | Subject to deviation: taxes included in price | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Quote validity | 98 days from bid due date | 100 days from bid due date | 98 days from bid due date | 103 days from bid due date | Compliant across bidders.
|  | Late payment interest rate (per month) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
5 | Contract Conditions | Warranty (48 months) | Deviation: 24 months only | Deviation: 24 months only | Deviation: 24 months only | Deviation: 24 months only | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Warranty reference point (FAT / PAC / Commissioning) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Warranty exclusions list (refractories, lances, etc.) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Completion period | 14 months from PO date | 16 months from PO date | 14 months from PO date | 13 months from PO date | Compliant across bidders.
|  | Performance Bank Guarantee (PBG) | Compliant: 10% PBG | Compliant: 10% PBG | Subject to deviation: 5% PBG only | Subject to deviation: 5% PBG only | Deviation: M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Liquidated damages | Subject to deviation: LD cap of 5% | Compliant: 0.5%/wk capped 10% | Subject to deviation: LD cap of 5% | Compliant: 0.5%/wk capped 10% | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
6 | Performance Guarantees (Technical) | Firing rate guarantee (MW for combustion lance) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Working volume guarantee (litres at nominal %) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Rotation speed range guarantee (RPM min-max) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Throughput / batch time guarantee |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Performance acceptance test criteria explicitly stated |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Field performance test arrangement (FAT / on-site) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
7 | Scope & Risks | Scope inclusions | Compliant: full SoW | Deviation: civil works excluded | Deviation: civil works excluded | Deviation: civil works excluded | Deviation: M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Scope exclusions | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Compliant across bidders.
|  | Refractory scope (vendor-supplied vs separate) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Deviations from RFQ | See Annex E — 5 commercial deviations | See Annex E — 2 commercial deviations | See Annex E — 5 commercial deviations | See Annex E — 5 commercial deviations | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Installation & commissioning | Compliant: I&C included | Compliant: I&C included | Deviation: I&C as separate optional package | Compliant: I&C included | Deviation: M/s. Outotec
|  | Insurance liability terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | IP / Technology licence terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
8 | Final Evaluation | Commercial acceptability | Acceptable subject to considering deviations | Not Acceptable | Acceptable subject to considering deviations | Not Acceptable | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Risk level | Medium | High | Medium | High | Compliant across bidders.
9 | Commercial Acceptability: Acceptable / Not Acceptable |  | Acceptable subject to considering deviations | Not Acceptable — bidder fails qualification gate | Acceptable subject to considering deviations | Not Acceptable — bidder fails qualification gate | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TSF TE
|  | BID ANALYSIS - TECHNICAL | [6 empty] | CONFIDENTIAL
CLIENT : | Glencore Technology |  |  |  |  | EQUIPMENT/SYSTEM: | TSF |  | TABLE - 7
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  | ENQ. NO.: | TCE/2026/ENQ/4471 | JOB NO.: | 14734A |  | SHEET 7 OF 9
SL.NO. | DETAILS | UNIT | BIDDER >> |  | VENDOR RESPONSES |  |  |  | REMARKS
|  |  | TCE SPEC. ↓ | Reference Value (TCE Study) | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | FURNACE DESIGN | No. | Number of Furnaces | 1 | 1.0454 | 1.0495 | 1.0139 | 0.9474 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | - | Furnace Type | Top Submerged Lance Smelting | Top Submerged Lance Smelting | Top Submerged Lance Smelting | Top Submerged Lance Smelting | Top Submerged Lance Smelting | All vendors compliant with TCE spec.
|  | m2 | Hearth Area | TBD per TCE study | Vendor to specify |  |  |  | Not specified by M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | TPH | Smelting Rate (concentrate) | 50 | 52.268 | 52.476 | 50.696 | 47.372 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
2 | PROCESS CYCLE | - | Operation Mode | Continuous | Continuous | Continuous | Continuous | Continuous | All vendors compliant with TCE spec.
|  | yr | Refractory Campaign Life | 2 | 2.0907 | 2.099 | 2.0278 | 1.8949 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | % | Annual Availability | 92 | 96.1731 | 96.5558 | 93.2806 | 87.1645 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
3 | LANCE & OPERATING CONDITIONS | - | Lance Type | Submerged top-blown | Submerged top-blown | Submerged top-blown | Submerged top-blown | Submerged top-blown | All vendors compliant with TCE spec.
|  | mm | Lance Immersion Depth | 300 | 313.608 | 314.856 | 304.176 | 284.232 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | % | Oxygen Enrichment | 50 | 52.268 | 52.476 | 50.696 | 47.372 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | Nm3/h | Lance Air Flow | 12000 | 12544.32 | 12594.24 | 12167.04 | 11369.28 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | - | Auxiliary Fuel | Natural Gas / coal fines | Natural Gas / coal fines | Natural Gas / coal fines | Natural Gas / coal fines | Natural Gas / coal fines | All vendors compliant with TCE spec.
|  | °C | Operating Temperature | 1200 | 1254.432 | 1259.424 | 1216.704 | 1136.928 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
4 | SLAG & MATTE CHEMISTRY | wt% | Target Matte Grade | 60 | 62.7216 | 62.9712 | 60.8352 | 56.8464 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | wt% | Final Slag Cu Content | 0.8 | 0.8363 | 0.8396 | 0.8111 | 0.758 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | - | Fe/SiO2 in Slag | 1.3 | 1.359 | 1.3644 | 1.3181 | 1.2317 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
|  | °C | Slag Tap Temperature | 1180 | 1233.5248 | 1238.4336 | 1196.4256 | 1117.9792 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
5 | MECHANICAL FEATURES | - | Refractory Lining | Mag-chrome basic brick | Mag-chrome basic brick | Mag-chrome basic brick | Mag-chrome basic brick | Mag-chrome basic brick | All vendors compliant with TCE spec.
|  | - | Lance Hoist System | Hydraulic with positioning control | Hydraulic with positioning control | Hydraulic with positioning control | Hydraulic with positioning control | Hydraulic with positioning control | All vendors compliant with TCE spec.
|  | - | Freeboard Burners | Natural gas fired | Natural gas fired | Natural gas fired | Natural gas fired | Natural gas fired | All vendors compliant with TCE spec.
|  | - | Concentrate Feed System | Belt + weigh feeders to roof port | Belt + weigh feeders to roof port | Belt + weigh feeders to roof port | Belt + weigh feeders to roof port | Belt + weigh feeders to roof port | All vendors compliant with TCE spec.
6 | TAPPING SYSTEM | - | Matte Taphole Design | Water-cooled copper block | Water-cooled copper block | Water-cooled copper block | Water-cooled copper block | Water-cooled copper block | All vendors compliant with TCE spec.
|  | - | Slag Taphole Design | Water-cooled copper block, separate level | Water-cooled copper block, separate level | Water-cooled copper block, separate level | Water-cooled copper block, separate level | Water-cooled copper block, separate level | All vendors compliant with TCE spec.
|  | /shift | Tap Frequency | 6 | 6.2722 | 6.2971 | 6.0835 | 5.6846 | M/s. Mitsui Mining & Smelting: -5.3% vs TCE
7 | OFF-GAS TREATMENT | - | Waste Heat Boiler | Forced circulation, steam generation | Forced circulation, steam generation | Forced circulation, steam generation | Forced circulation, steam generation | Forced circulation, steam generation | All vendors compliant with TCE spec.
|  | - | Gas Cooling | Evaporative + ID fan | Evaporative + ID fan | Evaporative + ID fan | Evaporative + ID fan | Evaporative + ID fan | All vendors compliant with TCE spec.
|  | - | Dedusting System | ESP, dust recycle | ESP, dust recycle | ESP, dust recycle | ESP, dust recycle | ESP, dust recycle | All vendors compliant with TCE spec.
|  | - | SO2 Handling | To single contact acid plant | To single contact acid plant | To single contact acid plant | To single contact acid plant | To single contact acid plant | All vendors compliant with TCE spec.
8 | INTEGRATION | - | Matte Routing | Matte ladles to TBRC | Matte ladles to TBRC | Matte ladles to TBRC | Matte ladles to TBRC | Matte ladles to TBRC | All vendors compliant with TCE spec.
|  | - | Slag Routing | Granulation / slag mill circuit | Granulation / slag mill circuit | Granulation / slag mill circuit | Granulation / slag mill circuit | Granulation / slag mill circuit | All vendors compliant with TCE spec.
|  | - | Dust Recycle | ESP dust back to feed | ESP dust back to feed | ESP dust back to feed | ESP dust back to feed | ESP dust back to feed | All vendors compliant with TCE spec.
|  | - | Acid Plant Coupling | Off-gas to H2SO4 plant | Off-gas to H2SO4 plant | Off-gas to H2SO4 plant | Off-gas to H2SO4 plant | Off-gas to H2SO4 plant | All vendors compliant with TCE spec.
9 | LIST OF DOCUMENT
A |  |  | Process Description |  | ✓ Included | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. Outotec
B |  |  | Substance list |  | ✓ Included | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. Mitsui Mining & Smelting
C |  |  | Plant emission list |  | ✓ Included | ✗ Missing | ✓ Included | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
D |  |  | Delivery lead time |  | ✗ Missing | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
E |  |  | Equipment List including noise emissions |  | ✓ Included | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. Outotec
F |  |  | Plant equipment 3D Model |  | ✓ Included | ✓ Included | ✓ Included | ✗ Missing | Missing from: M/s. Mitsui Mining & Smelting
G |  |  | Loading Diagrams |  | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
H |  |  | General Arrangement Drawings |  | ✗ Missing | ✓ Included | ✓ Included | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd.
I |  |  | Electrical Consumer List |  | ✓ Included | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
J |  |  | I/O Count based on past projects |  | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
K |  |  | Typical P&ID based on past projects |  | ✓ Included | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TRF CASTING WHEEL CE
|  | BID ANALYSIS - COMMERCIAL |  |  |  |  | CONFIDENTIAL
CLIENT : | Glencore Technology | [5 empty] | TABLE - 8A
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  |  |  | JOB NO.: | 14734A
RECOMMENDATION FOR AWARD OF JOB
SL NO. | BIDDERS REPLIES / QUOTE → |  | VENDOR RESPONSES |  |  |  | REMARKS
| DATA REQUIRED TO BE FURNISHED BY BIDDERS AS PER TENDER ↓ | TENDER REQUIREMENT ↓ | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | Bid Qualification | Net Worth | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
|  | Annual Turnover | QUALIFIED: Avg annual turnover INR 997 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 883 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 1029 Cr over last 3 FY | QUALIFIED: Avg annual turnover INR 1142 Cr over last 3 FY | All bidders qualified.
|  | Net Profit (PAT) | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | QUALIFIED: positive per FY2024-25 audited annual report | All bidders qualified.
2 | Proposal compliance | EMD of INR XXX (Indian Rupees YYYYY only) for Indian Bidders or USD XXXX (U.S. Dollars YYYYY) for Foreign Bidders. (Annexure X) | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: EMD value short of tender requirement | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Power of Attorney in favour of the person who has signed the bid | Compliant: PoA in favour of signatory attached | Deviation: PoA not notarised | Compliant: PoA in favour of signatory attached | Deviation: PoA not notarised | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | RFQ acceptance | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Compliant: RFQ terms accepted | Subject to deviation: noted in Annex D | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Deviation list | Compliant: Deviation list submitted | Subject to deviation: partial list | Compliant: Deviation list submitted | Compliant: Deviation list submitted | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
3 | Price Evaluation | Total price (Lump sum) | INR 8,97,00,000 Lump sum | INR 14,83,00,000 Lump sum | INR 12,79,00,000 Lump sum | INR 5,92,00,000 Lump sum | Compliant across bidders.
|  | Itemised pricing | Deviation: itemised pricing not provided | Deviation: itemised pricing not provided | Deviation: itemised pricing not provided | Deviation: itemised pricing not provided | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Front-End Engineering & Design (FEED) price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Core furnace package price (Groups 100-900) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Recommended spares price |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Shipping, Installation & Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Hot Commissioning |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | 2-year O&M spares & consumables | 2-year O&M spares: INR 3.7 Cr | 2-year O&M spares: INR 3.3 Cr | 2-year O&M spares: INR 1.9 Cr | 2-year O&M spares: INR 3.2 Cr | Compliant across bidders.
|  | Quote Currency (INR / USD / EUR / GBP) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
4 | Commercial Terms | Delivery terms (FCA) | Compliant: FCA Mumbai | Deviation: quoted on CIF basis | Compliant: FCA Mumbai | Deviation: quoted on CIF basis | Deviation: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
|  | Delivery schedule | 37 weeks ex-works from PO | 23 weeks ex-works from PO | 29 weeks ex-works from PO | 22 weeks ex-works from PO | Compliant across bidders.
|  | Payment terms | Subject to deviation: requesting 20% advance | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Subject to deviation: requesting 20% advance | Compliant: 10% advance, 80% pro-rata, 10% on PAC | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
|  | Payment milestone structure (PO / FAT / Commissioning split) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Taxes & duties | Compliant: GST 18% extra | Subject to deviation: taxes included in price | Compliant: GST 18% extra | Compliant: GST 18% extra | Deviation: M/s. JNK India Pvt. Ltd.
|  | Quote validity | 107 days from bid due date | 113 days from bid due date | 99 days from bid due date | 92 days from bid due date | Compliant across bidders.
|  | Late payment interest rate (per month) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
5 | Contract Conditions | Warranty (48 months) | Compliant: 48 months from PAC | Deviation: 24 months only | Compliant: 48 months from PAC | Compliant: 48 months from PAC | Deviation: M/s. JNK India Pvt. Ltd.
|  | Warranty reference point (FAT / PAC / Commissioning) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Warranty exclusions list (refractories, lances, etc.) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Completion period | 17 months from PO date | 17 months from PO date | 15 months from PO date | 14 months from PO date | Compliant across bidders.
|  | Performance Bank Guarantee (PBG) | Subject to deviation: 5% PBG only | Compliant: 10% PBG | Compliant: 10% PBG | Compliant: 10% PBG | Deviation: M/s. ISGEC Heavy Engineering Ltd.
|  | Liquidated damages | Subject to deviation: LD cap of 5% | Compliant: 0.5%/wk capped 10% | Compliant: 0.5%/wk capped 10% | Subject to deviation: LD cap of 5% | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. Mitsui Mining & Smelting
6 | Performance Guarantees (Technical) | Firing rate guarantee (MW for combustion lance) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Working volume guarantee (litres at nominal %) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Rotation speed range guarantee (RPM min-max) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Throughput / batch time guarantee |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Performance acceptance test criteria explicitly stated |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Field performance test arrangement (FAT / on-site) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
7 | Scope & Risks | Scope inclusions | Compliant: full SoW | Deviation: civil works excluded | Deviation: civil works excluded | Compliant: full SoW | Deviation: M/s. JNK India Pvt. Ltd., M/s. Outotec
|  | Scope exclusions | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Site civil works, utility tie-ins, taxes | Compliant across bidders.
|  | Refractory scope (vendor-supplied vs separate) |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Deviations from RFQ | See Annex E — 4 commercial deviations | See Annex E — 5 commercial deviations | See Annex E — 6 commercial deviations | See Annex E — 4 commercial deviations | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Installation & commissioning | Deviation: I&C as separate optional package | Deviation: I&C as separate optional package | Deviation: I&C as separate optional package | Deviation: I&C as separate optional package | Deviation: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Insurance liability terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | IP / Technology licence terms |  |  |  |  | Not stated: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
8 | Final Evaluation | Commercial acceptability | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
|  | Risk level | Medium | Medium | Medium | Medium | Compliant across bidders.
9 | Commercial Acceptability: Acceptable / Not Acceptable |  | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Acceptable subject to considering deviations | Not acceptable: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE

## TRF CASTING WHEEL TE
|  | BID ANALYSIS - TECHNICAL | [6 empty] | CONFIDENTIAL
CLIENT : | Glencore Technology |  |  |  |  | EQUIPMENT/SYSTEM: | TRF_CASTING_WHEEL |  | TABLE - 9
PROJECT : | Anode Smelter Plant (TRF + TBRC + TSF + Casting Wheel) |  |  | ENQ. NO.: | TCE/2026/ENQ/4471 | JOB NO.: | 14734A |  | SHEET 9 OF 9
SL.NO. | DETAILS | UNIT | BIDDER >> |  | VENDOR RESPONSES |  |  |  | REMARKS
|  |  | TCE SPEC. ↓ | Reference Value (TCE Study) | M/s. ISGEC Heavy Engineering Ltd. | M/s. JNK India Pvt. Ltd. | M/s. Outotec | M/s. Mitsui Mining & Smelting
1 | WHEEL DESIGN | No. | Number of Casting Wheels | 1 | 1.0175 | 0.9386 | 1.0574 | 0.9385 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | - | Wheel Type | Horizontal rotary | Horizontal rotary | Horizontal rotary (vendor compliant) | Horizontal rotary | Horizontal rotary | All vendors compliant with TCE spec.
|  | No. | Number of Moulds | 22 | 22.3854 | 20.6483 | 23.2637 | 20.6466 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | m | Wheel Diameter | 12 | 12.2102 | 11.2627 | 12.6893 | 11.2618 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | - | Mould Material | Copper, water-cooled | Copper, water-cooled | Copper, water-cooled (vendor compliant) | Copper, water-cooled | Copper, water-cooled | All vendors compliant with TCE spec.
2 | CASTING CYCLE | anodes/h | Casting Rate | 80 | 81.4016 | 75.0848 | 84.5952 | 75.0784 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | kg | Anode Weight | 400 | 407.008 | 375.424 | 422.976 | 375.392 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | mm | Anode Dimensions | 1000 × 970 × 45 | 1000 × 970 × 45 | 1000 × 970 × 45 (vendor compliant) | 1000 × 970 × 45 | 1000 × 970 × 45 | All vendors compliant with TCE spec.
|  | % | Anode Rejection Rate | 3 | 3.0526 | 2.8157 | 3.1723 | 2.8154 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
3 | MOULD OPERATION | - | Mould Cooling | Air + Water cooling | Air + Water cooling | Air + Water cooling (vendor compliant) | Air + Water cooling | Air + Water cooling | All vendors compliant with TCE spec.
|  | - | Mould Wash Type | Yotai Coat COAT-NCF | Yotai Coat COAT-NCF | Yotai Coat COAT-NCF (vendor compliant) | Yotai Coat COAT-NCF | Yotai Coat COAT-NCF | All vendors compliant with TCE spec.
|  | kg/t Cu | Mould Wash Consumption | 0.15 | 0.1526 | 0.1408 | 0.1586 | 0.1408 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.1% vs TCE
|  | casts | Mould Life | 8000 | 8140.16 | 7508.48 | 8459.52 | 7507.84 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | °C | Mould Surface Temp (before) | 150 | 152.628 | 140.784 | 158.616 | 140.772 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
4 | ANODE QUALITY | % | Anode Weight Tolerance | 1.5 | 1.5263 | 1.4078 | 1.5862 | 1.4077 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | - | Surface Finish | Smooth, free of laps and cracks | Smooth, free of laps and cracks | Smooth, free of laps and cracks (vendor compliant) | Smooth, free of laps and cracks | Smooth, free of laps and cracks | All vendors compliant with TCE spec.
|  | - | Ear Geometry Compliance | ISAKIDD™ compatible | ISAKIDD™ compatible | ISAKIDD™ compatible (vendor compliant) | ISAKIDD™ compatible | ISAKIDD™ compatible | All vendors compliant with TCE spec.
5 | MECHANICAL FEATURES | - | Wheel Drive System | Hydraulic with variable speed | Hydraulic with variable speed | Hydraulic with variable speed (vendor compliant) | Hydraulic with variable speed | Hydraulic with variable speed | All vendors compliant with TCE spec.
|  | - | Pouring Launder | Tilting launder with weigh control | Tilting launder with weigh control | Tilting launder with weigh control (vendor compliant) | Tilting launder with weigh control | Tilting launder with weigh control | All vendors compliant with TCE spec.
|  | - | Stripping Mechanism | Pneumatic stripper with tipping | Pneumatic stripper with tipping | Pneumatic stripper with tipping (vendor compliant) | Pneumatic stripper with tipping | Pneumatic stripper with tipping | All vendors compliant with TCE spec.
6 | COOLING & WATER SYSTEM | m3/h | Cooling Water Flow | 800 | 814.016 | 750.848 | 845.952 | 750.784 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | °C | Water Temperature Rise | 15 | 15.2628 | 14.0784 | 15.8616 | 14.0772 | M/s. JNK India Pvt. Ltd.: -6.1% vs TCE; M/s. Outotec: +5.7% vs TCE; M/s. Mitsui Mining & Smelting: -6.2% vs TCE
|  | - | Closed-loop Cooling | Yes, with cooling tower | Yes, with cooling tower | Yes, with cooling tower (vendor compliant) | Yes, with cooling tower | Yes, with cooling tower | All vendors compliant with TCE spec.
7 | STRIPPING & WEIGHING | - | Stripping Method | Mechanical with stripping hammer | Mechanical with stripping hammer | Mechanical with stripping hammer (vendor compliant) | Mechanical with stripping hammer | Mechanical with stripping hammer | All vendors compliant with TCE spec.
|  | - | Anode Weighing | ±0.5%, auto-weigh per anode | ±0.5%, auto-weigh per anode | ±0.5%, auto-weigh per anode (vendor compliant) | ±0.5%, auto-weigh per anode | ±0.5%, auto-weigh per anode | All vendors compliant with TCE spec.
|  | - | Anode Stacking | Robotic stacker to dispatch | Robotic stacker to dispatch | Robotic stacker to dispatch (vendor compliant) | Robotic stacker to dispatch | Robotic stacker to dispatch | All vendors compliant with TCE spec.
8 | INTEGRATION | - | Feed from TRF | Liquid copper via tilting launder | Liquid copper via tilting launder | Liquid copper via tilting launder (vendor compliant) | Liquid copper via tilting launder | Liquid copper via tilting launder | All vendors compliant with TCE spec.
|  | - | Anode Dispatch | To ISAKIDD™ Tankhouse | To ISAKIDD™ Tankhouse | To ISAKIDD™ Tankhouse (vendor compliant) | To ISAKIDD™ Tankhouse | To ISAKIDD™ Tankhouse | All vendors compliant with TCE spec.
|  | - | Rejected Anode Recycle | Back to TRF charge | Back to TRF charge | Back to TRF charge (vendor compliant) | Back to TRF charge | Back to TRF charge | All vendors compliant with TCE spec.
|  | - | Control System Tie-in | Common DCS with TRF | Common DCS with TRF | Common DCS with TRF (vendor compliant) | Common DCS with TRF | Common DCS with TRF | All vendors compliant with TCE spec.
9 | LIST OF DOCUMENT
A |  |  | Process Description |  | ✓ Included | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec
B |  |  | Substance list |  | ✓ Included | ✗ Missing | ✓ Included | ✗ Missing | Missing from: M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
C |  |  | Plant emission list |  | ✗ Missing | ✗ Missing | ✓ Included | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
D |  |  | Delivery lead time |  | ✓ Included | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. Outotec
E |  |  | Equipment List including noise emissions |  | ✗ Missing | ✗ Missing | ✓ Included | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Mitsui Mining & Smelting
F |  |  | Plant equipment 3D Model |  | ✓ Included | ✗ Missing | ✗ Missing | ✓ Included | Missing from: M/s. JNK India Pvt. Ltd., M/s. Outotec
G |  |  | Loading Diagrams |  | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
H |  |  | General Arrangement Drawings |  | ✗ Missing | ✓ Included | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
I |  |  | Electrical Consumer List |  | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. JNK India Pvt. Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
J |  |  | I/O Count based on past projects |  | ✗ Missing | ✓ Included | ✗ Missing | ✓ Included | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec
K |  |  | Typical P&ID based on past projects |  | ✗ Missing | ✓ Included | ✗ Missing | ✗ Missing | Missing from: M/s. ISGEC Heavy Engineering Ltd., M/s. Outotec, M/s. Mitsui Mining & Smelting
Proprietary Notice and Version Control: This document contains confidential information for use only by the "Client"; for the Project under consideration, which is provided for the sole purpose of permitting the recipient to evaluate the information submitted herewith. In consideration of receipt of this document; unless agreed to in contrary in the Contract; the recipient agrees to maintain such information in confidence and to not reproduce or otherwise disclose this information to any person outside the recipient's organisation; except that there is no obligation to maintain the confidentiality of any information which was known to the recipient prior to receipt of such information from Tata Consulting Engineers Limited, or becomes publicly known through no fault of recipient, or Tata Consulting Engineers Limited, or is received without obligation of confidentiality from a third party owing no obligation of confidentiality to Tata Consulting Engineers Limited. All information given under this version over rides all and any kind of offers, assumptions, deliverables and contracts submitted verbally (and subsequently communicated in writing) or in writing or otherwise given under any and all previous version/s.
REVISIONS | REV. NO. |  |  |  | TATA CONSULTING ENGINEERS LIMITED
PPD. BY
CHD. BY
APD. BY
DATE